## Sheet1
Pages	Developer Start Date	Developer End Date	Developer No. of Days	Developers	Designer Start Date	Designer End Date	Designer No. of Days	Designer	Total No. of Days	Comments
Site Setup & Configuration Local and development	Feb 22, 2016	Feb 23, 2016	2	Pooja					2
Header & Footer Integration			4	Pooja					4	It is dependent on Ektron. The functionality needs to be built in Ektron.
Expert-Guide----Main-Page					Feb 25, 2016	Feb 26, 2016	2	Mangesh	4
Search Section	Feb 24, 2016	Feb 24, 2016	1	Pooja
Featured Expert Section	Feb 25, 2016	Feb 25, 2016	1	Pooja
A-to-Z-Expert-Directory					Mar 1, 2016	Mar 2, 2016	2	Mangesh	4
Expert Listing	Feb 26, 2016	Feb 26, 2016	1	Pooja
Expert Search Section	Feb 29, 2016	Feb 29, 2016	0.5	Pooja
Expert Home Link	Feb 29, 2016	Feb 29, 2016	0.5	Pooja
Expertise-Top-Level					Mar 4, 2016	Mar 7, 2016	2	Mangesh	5
Alphabets List	Mar 1, 2016	Mar 1, 2016	1	Pooja
Expertise List Alphabetically	Mar 2, 2016	Mar 2, 2016	1	Pooja
Expert Home Link and View Experts A to Z link	Mar 3, 2016	Mar 3, 2016	0.5	Pooja
Expert Search Section	Mar 3, 2016	Mar 3, 2016	0.5	Pooja
Expert-Guide----Expertise-Main-Page					Mar 8, 2016	Mar 8, 2016	1	Mangesh	3
Expert List based on Expertise	Mar 4, 2016	Mar 4, 2016	1	Pooja
Expert Home Link and View all expertise link	Mar 7, 2016	Mar 7, 2016	0.5	Pooja
Expert Search Section	Mar 7, 2016	Mar 7, 2016	0.5	Pooja
Expert-Guide-----Individual-Expert-Page					Mar 11, 2016	Mar 15, 2016	3	Mangesh	7
Creation of Publications and contents	Mar 8, 2016	Mar 8, 2016	0.75	Pooja
Creation of Resources and contents	Mar 8, 2016	Mar 9, 2016	0.75	Pooja
Creation of Engagement and Classes	Mar 9, 2016	Mar 10, 2016	0.75	Pooja
Creation of Media Appearances	Mar 10, 2016	Mar 10, 2016	0.75	Pooja
Expert Search Section and Expert A-Z link	Mar 11, 2016	Mar 11, 2016	0.5	Pooja
Expert detail description	Mar 11, 2016	Mar 11, 2016	0.25	Pooja